## Slide 1
Activity 3: How to set properties about a Project Plan?
1. On the File menu, click info, Click the project information , select Advanced properties
2. In the properties dialog box, click the Summary tab, and then enter the information you want like:
● Title of the Project
● Manager of the Project
● Company Information
● Any other useful information in comments

## Slide 3
Activity 2: How to set working & non-working time?
The primary means by which each task and resource can be scheduled to work in the project. The project calendar defines the general working & non-working time for tasks.
Click On the project, click Change Working Time.
In the For Calendar box, select the base calendar you want to edit (normally it is Standard)
In the Name field on Exception tab, enter a descriptive name for the non-working time, such as Holiday
In the Start and Finish fields, type or select the start and finish dates for the non-working time span.
Active “Work Weeks” tab and then click Details button to change the default non-working days and timing
Click OK

## Slide 4
In a task entry table, enter a name for mile stone and in the duration field enter 0day and then press “ENTER”
Milestones are significant (important) events that are either reached in the project or imposed on the project. Because the milestone normally does not include any work, so presented as task with ZERO duration

## Slide 5
Activity 5: How to organize tasks into phases?
  Organize groups of closely related tasks
  Duration, start date or other calculated values of a summery task cannot be changed
Select the names of tasks to become subtasks of a summary task
On the project menu point to outline and then click indent