## Slide 1: LAB 4

## Slide 2: TODAY TASKS
  1. Making a Milestone
A milestone is a task with zero duration; it is generally used for tracking purposes
  2. Entering Recurring Tasks
3. Creating a basic WORK BREAKDOWN STRUCTURE (WBS)
  Entering the List of Tasks
  Creating a unique WBS Code
    4. Network Diagram
    5. Assigning Predecessors to Tasks

## Slide 3
Possible relationships (links) among different tasks are:
● Finish-to-Start (FS) – Default, commonly used
● Start-to-Start (SS) (having same start dates)
● Finish-to-Finish (FF) (having same finish dates)
● Start-to-Finish (SF) (rarely used)

## Slide 4
Double‐click the task that needs the predecessors. Select the Predecessors & enter the ID for the task on which selected task is dependent & then select the type of dependency needed.

## Slide 6: Project Elements
Project
Activity
Activity
Activity
Activity
Activity
Activity
Task
Task
Function
Function
Management Activity
Duration – Project Life
  Risk Management
  Configuration
Management
Activity
– An element of work with expected duration, cost, and resources
Task
Lowest level of work
No shown on WBS

## Slide 7: Work Breakdown Structure: WBS
Hierarchical list of project’s work activities
  List of Activities, not Things
2 Formats
  Outline (indented format)
  Graphical Tree (Organizational Chart)
Uses a decimal numbering system
– e.g., 3.1.5
  0 is typically top level
Includes
  Development, management, and project support activities
Shows “is contained in” relationships
Does not show dependencies or durations

## Slide 8: WBS Chart Example

## Slide 9: WBS Outline Example
0.0 Retail Web Site
1.0 Project Management
2.0 Requirements Gathering
3.0 Analysis & Design
  Site Software Development
  HTML Design and Creation
  Backend Software
    Database Implementation
    Middleware Development
    Security Subsystems
    Catalog Engine
    Transaction Processing
  Graphics and Interface
  Content Creation
5.0 Testing and Production

## Slide 10: Outline WBS w/Gantt

## Slide 11: Why do we require a Work Breakdown Structure?
To organize the work to be done
To illustrate the work to be done
To assure that all necessary work has been identified
To divide the work into small, well defined tasks
To facilitate planning, estimating and scheduling of the project
To provide a basis for data monitoring and historical data collection
To identify contractual tasks and deliverables

## Slide 12: Why WBS
Cost estimating
  To make sure all activities get estimated
  To make sure that each element of the estimate corresponds to a necessary activity
  To “roll up” costs of individual elements into total costs for sub-elements and for the system as a whole
Cost accounting
  To assign work and “charge it” to appropriate cost centers based on specific WBS elements
  To determine the actual cost of each element
Schedule performance
  To monitor which activities are complete
  To measure project progress

## Slide 13: WBS Types
Process WBS
  a.k.a. Activity-oriented
  e.g., Requirements, Analysis, Design, Testing
  Typically used by PM
Product WBS
  a.k.a. Entity-oriented
  e.g., Financial engine, Interface system, DB
  Typically used by engineering manager

## Slide 14: Process WBS

## Slide 15: Product WBS

## Slide 16: WBS Types
Less frequently used alternatives
Organizational WBS
  Research, Product Design, Engineering, Operations
  Can be useful for highly cross-functional projects
Geographical WBS
  Can be useful with distributed teams
  ISB team, NYC team, MAN team

## Slide 17: Work Packages
Generic term for discrete tasks with definable end results
Typically the “leaves” on the tree
The “one-to-two” rule
  Often at: 1 or 2 persons for 1 or 2 weeks
Basis for monitoring and reporting progress
  Can be tied to budget items (charge numbers)
  Resources (personnel) assigned
For software development project correspond to the lowest identifiable objects or modules to be created in a deliverable system

## Slide 18: WBS Techniques
Top-Down
Bottom-Up
Analogy
Rolling Wave
  1st pass: go 1-3 levels deep
  Gather more requirements or data
  Add more detail later
Post-its on a wall

## Slide 19: WBS Techniques - Top-down
Start at highest level
Systematically develop increasing level of detail
Best if
  The problem is well understood
  Technology and methodology are not new
  This is similar to an earlier project or problem
But is also applied in majority of situations

## Slide 20: WBS Techniques - Bottom-up
Start at lowest level tasks
Aggregate into summaries and higher levels
Cons
  Time consuming
  Needs more requirements complete
Pros
  Detailed

## Slide 21: WBS Techniques - Analogy
Base WBS upon that of a “similar” project
Use a template
Analogy also can be estimation basis
Pros
  Based on past actual experience
Cons
  Needs comparable project

## Slide 22: WBS Techniques - Brainstorming
Generate all activities you can think of that need to be done
Group them into categories
Both Top-down and Brainstorming can be used on the same WBS
Remember to get the people who will be doing the work involved